## Sheet1
SPRINT #1 Burndown Chart
Duration: 5 Days
Task ID | Task Name | Expected Time (Hours) | 2025-06-25 | 2025-06-26 | 2025-06-27 | 2025-06-28 | 2025-06-29
1 | Plan Project | 0.5 | 0.5
2 | Write User Stories | 1 | 1
3 | Create Burndown Chart | 0.5 | 0.5
4 | Write Agile section of the Report | 1 | 1
5 | Building the Robot | 1 |  | 1
6 | Display images on led matrix | 3 |  | 3
7 | Recognize faces | 4 |  |  | 4
8 | Protect faces data | 3 |  |  | 1 | 2
9 | Complete a video presentation of the project | 2 |  |  |  | 1 | 1
10 | Complete a final Report | 2 |  |  |  |  | 2
| TOTAL | 18
| Expected | 18 | 3 | 4 | 5 | 3 | 3
| Remaining (E) | 18 | 15 | 11 | 6 | 3 | 0
| ACTUAL | 0 | 4.5 | 3 | 0 | 8.5 | 2
| Remaining (A) | 0 | 13.5 | 10.5 | 10.5 | 2 | 0